## Initiatives tracker 6-2026
Initiatives Tracker - status as of end June 2026
[5 empty] | (Not started, On Track, Delay, Deprioritized, Live) | (Flag if status change from last month) |  |  | (High, Medium, Low)
No | Initiative Names | Timing | Expected impact | PIC | Status | Status change | New timing (if applicable) | Details from that month | How confident
Strategic unlock
1 | Add 1 partner with higher risk appetite | May-26 | %Eligible/Total User Base +10pp | Persona 1 | Live | Yes |  | Integration and UAT finished in April 2026; pilot ready in mid-May 2026, now live. | High
2 | Add 1 partner with higher risk appetite | Aug-26 | %Eligible/Total User Base +10pp | Persona 1 | Delay | Yes | Sep-26 | Partner agreed to phased rollout; Phase 1 (1M users) target delayed by 2 weeks from original Aug 31 plan due to dev re-estimation, now targeting late September. | Medium
3 | New modelling allows scoring new segments | Sep-26 | %Eligible/Total User Base +15pp | Persona 2 | On Track | No |  | Model v1 optimized with Gini increased to 0.3; data team in final steps to launch as planned in September. | High
4 | Add new product that unlock new demand | May-26 | %Traffic/Eligible +10pp | Persona 3 | Live | Yes | Jun-26 | UAT completed May 31; deployment finished and product went live on June 7, 2026. | High
Incremental improvements
5 | New score model version allows incremental more Eligible in existing segment & increasing Approval Rate | Apr-26 | (1) %Eligible/Total User Base +5pp (2) %Approval Rate +10pp | Persona 2 | Live | Yes | May-26 | Model v-next deployed in May 2026; absolute approval rate currently at 65% vs 70% target, remediation in progress. | High
6 | Discover new traffic channel #1 | Mar-26 | %Traffic/Eligible +2pp | Persona 3 | Live | No |  | Traffic channel #1 launched in March 2026 and remains live. | High
7 | Discover new traffic channel #2 | Jul-26 | %Traffic/Eligible +2pp | Persona 3 | Deprioritized | Yes | Q4-2026 | Deprioritized due to Cashier team resource constraints and performance test instability; rescheduled to Q4 2026. | Medium
8 | Revamp layout of Landing Page | Feb-26 | %Submission/Traffic +2pp | Persona 1 | Live | No |  | Landing page layout revamped and launched in February 2026. | High
9 | Make product offerings more diverse | Mar-26 | (1) %Submission/Traffic +2pp (2) Average Ticket size +10% | Persona 1 | Live | No |  | Product offerings diversification launched in March 2026. | High
10 | Personalize offerings per users using big data | Jul-26 | %Submission/Traffic +2pp | Persona 2 | Delay | Yes | Aug-26 | Kickoff delayed to end of June due to Data Science team prioritizing model optimization; estimated 2 months duration to complete. | Medium
11 | New redirecting tactics for dropped customers | Oct-26 | %Submission/Traffic +0.5pp | Persona 3 | Deprioritized | No | Q4-2026 | Deprioritized due to low expected impact; may be revisited in Q4 2026. | High
12 | Running year-end campaign | Q4/2026 | %Traffic/Eligible +5pp | Persona 3 | Not started | No |  | Planning to begin in Q3; creative and budget not yet locked. | Low