CL - Biz - Report 2026.06

Cash Loan (CL) monthly business report  •  Reporting month: June 2026  •  Latest actual: Jun-26  •  Forecast month: Jul-26

Data basis. Figures are drawn from the Annual Plan / KPI sheet and the Initiative Tracker (status as of end-June 2026). Structure follows the fixed four-part format; each section is split into Structural ceiling unlocks and Incremental acquisition / retention improvements.

AI-generated. This report was produced automatically by an AI agent (narrative written by an LLM, figures computed deterministically). Review before use.

KPI snapshot — Cash Loan funnel

| Metric (Cash Loan) | Unit | May-26 | Jun-26 | MoM | Jun Plan | vs Plan |
| --- | --- | --- | --- | --- | --- | --- |
| Total User Base | 000 | 64 | 67 | +5% | 68 | On plan |
| %mom growth user base | % | 5% | 5% | 0pp | 5% | On plan |
| Eligible Base For Cash Loan | 000 | 22 | 23 | +5% | 24 | On plan |
| %Eligible/Total User Base | % | 35% | 35% | 0pp | 35% | On plan |
| Traffic to Landing Page | 000 | 7 | 10 | +38% | 10 | On plan |
| %Traffic/Eligible | % | 32% | 42% | +10pp | 42% | On plan |
| Submission | 000 | 1 | 1 | +38% | 1 | On plan |
| %Submission/Traffic | % | 14% | 14% | 0pp | 14% | On plan |
| Approved | 000 | 1 | 1 | +38% | 1 | -8% |
| %Approval Rate | % | 65% | 65% | 0pp | 70% | -5pp |
| Average Ticket Size | VNDm | 110 | 110 | 0% | 110 | On plan |
| %mom growth ticket size | % | 0% | 0% | 0pp | 0% |  |
| Disbursement Volume | VNDm | 71,543 | 98,596 | +38% | 107,191 | -8% |

Read: Disbursement Volume reached VNDm 98,596 in June 2026, up 38% MoM but 8% below the VNDm 107,191 plan. The funnel expanded mechanically via a 5% growth in Eligible Base For Cash Loan and a 38% surge in Traffic to Landing Page, while conversion rates remained flat. The primary variance to plan stems from a 5pp shortfall in %Approval Rate, as other levers met or exceeded targets.

Movement check: Eligible Base For Cash Loan +5% — MECHANICAL (base-driven; %Eligible/Total User Base flat). Traffic to Landing Page — REAL (%Traffic/Eligible +10pp). Submission +38% — MECHANICAL (base-driven; %Submission/Traffic flat). Approved +38% — MECHANICAL (base-driven; %Approval Rate flat).

# 1. Performance Overview and Analysis

Headline. Disbursement Volume grew 38% MoM to VNDm 98,596, driven by a 38% increase in Approved volume, yet missed the VNDm 107,191 plan by 8% due to a 5pp gap in %Approval Rate.

MoM bridge (fact). Disbursement Volume +38% decomposes into Eligible Base For Cash Loan x1.05 (mechanical base growth) and %Traffic/Eligible x1.31 (real lift from #4.0 Add new product that unlock new demand); %Submission/Traffic x1.00 and %Approval Rate x1.00 remained flat. Arithmetic: 1.05 x 1.31 x 1.00 x 1.00 ~= 1.38, i.e. +38%.

Plan-miss bridge (fact). The -8% miss vs plan is driven entirely by %Approval Rate at 65% vs 70% plan (-5pp), despite #5.0 New score model version allows incremental more Eligible in existing segment & increasing Approval Rate delivering its promised +10pp lift in May (held through Jun). All other levers (Eligible Base, Traffic, Submission, Ticket Size) are on plan.

Structural ceiling unlocks

Eligible Base For Cash Loan: +5% MoM (On plan) driven by mechanical base growth; #1.0 Add 1 partner with higher risk appetite realized +10pp in May (held through Jun), while #5.0 New score model version allows incremental more Eligible in existing segment & increasing Approval Rate realized +5pp in May (held through Jun).

%Approval Rate: Flat 0pp MoM at 65% (vs 70% plan); #5.0 New score model version allows incremental more Eligible in existing segment & increasing Approval Rate realized +10pp in May (held through Jun), leaving a residual 5pp gap unowned.

Incremental acquisition / retention improvements

Traffic to Landing Page: +38% MoM (On plan) driven by #4.0 Add new product that unlock new demand realizing +10pp in Jun (held through Jun) and #6.0 Discover new traffic channel #1 realizing +2pp in Mar (held through Jun).

Submission: +38% MoM (On plan) driven mechanically by traffic growth; #8.0 Revamp layout of Landing Page realized +2pp in Feb (held through Jun) and #9.0 Make product offerings more diverse realized +2pp in Mar (held through Jun).

Average Ticket Size: Flat 0% MoM (On plan); #9.0 Make product offerings more diverse realized +10% in Mar (held through Jun).

Initiative delivery — expected vs realized

| # | Initiative | Status | Promised | Realized | Verdict |
| --- | --- | --- | --- | --- | --- |
| 1.0 | Add 1 partner with higher risk appetite | Live | %Eligible/Total User Base +10pp | +10pp in May, held | realized in May (held through Jun) |
| 2.0 | Add 1 partner with higher risk appetite | Delay | %Eligible/Total User Base +10pp | — | not due (Delay) |
| 3.0 | New modelling allows scoring new segments | On Track | %Eligible/Total User Base +15pp | — | not due (On Track) |
| 4.0 | Add new product that unlock new demand | Live | %Traffic/Eligible +10pp | +10pp in Jun, held | realized in Jun (held through Jun) |
| 5.0 | New score model version allows incremental more Eligible in existing segment & increasing Approval Rate | Live | %Eligible/Total User Base +5pp; %Approval Rate +10pp | +5pp in May, held; +10pp in May, held | realized in May (held through Jun); realized in May (held through Jun) |
| 6.0 | Discover new traffic channel #1 | Live | %Traffic/Eligible +2pp | +2pp in Mar, held | realized in Mar (held through Jun) |
| 7.0 | Discover new traffic channel #2 | Deprioritized | %Traffic/Eligible +2pp | — | not due (Deprioritized) |
| 8.0 | Revamp layout of Landing Page | Live | %Submission/Traffic +2pp | +2pp in Feb, held | realized in Feb (held through Jun) |
| 9.0 | Make product offerings more diverse | Live | %Submission/Traffic +2pp; Average Ticket size +10% | +2pp in Mar, held; +10% in Mar, held | realized in Mar (held through Jun); realized in Mar (held through Jun) |
| 10.0 | Personalize offerings per users using big data | Delay | %Submission/Traffic +2pp | — | not due (Delay) |
| 11.0 | New redirecting tactics for dropped customers | Deprioritized | %Submission/Traffic +0.5pp | — | not due (Deprioritized) |
| 12.0 | Running year-end campaign | Not started | %Traffic/Eligible +5pp | — | not due (Not started) |

# 2. Next Month (July) Run-Rate and Key Initiatives

Run-rate. July disbursement run-rate is VNDm 103,525 (+5% MoM vs June actual), projecting a -23% miss vs the VNDm 134,754 July plan absent new structural unlocks.

Forecast — July funnel

| Metric (Cash Loan) | Unit | Jun-26 (actual) | Jul-26 (forecast) | Initiative notes |
| --- | --- | --- | --- | --- |
| Total User Base | 000 | 67 | 70 |  |
| % mom growth user base | % | 5% | 5% |  |
| Eligible Base For Cash Loan | 000 | 23 | 25 |  |
| % Eligible/Total User Base | % | 35% | 35% |  |
| Traffic to Landing Page | 000 | 10 | 10 |  |
| %Traffic/Eligible | % | 42% | 42% |  |
| Submission | 000 | 1 | 1 |  |
| %Submission/Traffic | % | 14% | 14% |  |
| Approved | 000 | 1 | 1 |  |
| % Approval Rate | % | 65% | 65% |  |
| Average Ticket Size | VNDm | 110 | 110 |  |
| % mom growth ticket size | % | 0% | 0% |  |
| Disbursement Volume | VNDm | 98,596 | 103,525 |  |

Structural ceiling unlocks

No new structural initiatives scheduled for July; #2.0 Add 1 partner with higher risk appetite delayed to Sep-26 and #3.0 New modelling allows scoring new segments on track for Sep-26.

Incremental acquisition / retention improvements

No new incremental initiatives scheduled for July; #10.0 Personalize offerings per users using big data delayed to Aug-26 and #12.0 Running year-end campaign not started until Q4/2026.

# 3. Top Priorities for Next Month (July)

| # | Objective / lever | Initiative & owner | Target outcome & why it matters |
| --- | --- | --- | --- |
| 1 | Structural — %Eligible/Total User Base | New modelling allows scoring new segments (Persona 2) | Unlock +15pp in %Eligible/Total User Base to expand the addressable market for Cash Loan, addressing the structural ceiling on Eligible Base For Cash Loan growth. |
| 2 | Structural — %Eligible/Total User Base | Add 1 partner with higher risk appetite (Persona 1) | Secure +10pp in %Eligible/Total User Base via partner integration to diversify risk appetite and increase the volume of users eligible for Cash Loan. |
| 3 | Incremental — %Traffic/Eligible | Running year-end campaign (Persona 3) | Drive +5pp in %Traffic/Eligible to maximize conversion of the existing eligible base into active applicants, mitigating the current traffic saturation. |

# 4. Progress Toward Annual Plan

Structural ceiling unlocks

| Lever | What landed / what's next | Confidence | Status |
| --- | --- | --- | --- |
| %Eligible/Total User Base | #1.0 Add 1 partner with higher risk appetite landed +10pp in May (held); #5.0 New score model version allows incremental more Eligible in existing segment & increasing Approval Rate landed +5pp in May (held). Next: #3.0 New modelling allows scoring new segments (Sep-26, +15pp) and #2.0 Add 1 partner with higher risk appetite (Sep-26, +10pp). | High | On track |
| %Approval Rate | #5.0 New score model version allows incremental more Eligible in existing segment & increasing Approval Rate landed +10pp in May (held). Next: No active initiatives; residual gap requires new remediation. | Medium | Behind |

Incremental acquisition / retention improvements

| Lever | What landed / what's next | Impact | Status |
| --- | --- | --- | --- |
| %Traffic/Eligible | #4.0 Add new product that unlock new demand landed +10pp in Jun (held); #6.0 Discover new traffic channel #1 landed +2pp in Mar (held). Next: #12.0 Running year-end campaign (Q4/2026, +5pp). | +12pp realized | On track |
| %Submission/Traffic | #8.0 Revamp layout of Landing Page landed +2pp in Feb (held); #9.0 Make product offerings more diverse landed +2pp in Mar (held). Next: #10.0 Personalize offerings per users using big data (Aug-26, +2pp). | +4pp realized | On track |
| Average Ticket Size | #9.0 Make product offerings more diverse landed +10% in Mar (held). Next: No active initiatives. | +10% realized | On track |

YTD vs plan and FY outlook

YTD Disbursement stands at VNDm 277,174 vs VNDm 339,865 plan (-18%); FY plan is VNDm 1,879,405. Hitting FY requires closing the %Approval Rate gap immediately and accelerating the Sep-26 structural initiatives (#2.0 and #3.0) to compensate for the Q2 shortfall.

Escalations — high-impact initiatives delayed / deprioritized

| Initiative | Owner | Status | Impact | New timing | Note |
| --- | --- | --- | --- | --- | --- |
| Add 1 partner with higher risk appetite | Persona 1 | Delay | %Eligible/Total User Base +10pp | Sep-26 | Partner agreed to phased rollout; Phase 1 (1M users) target delayed by 2 weeks from original Aug 31 plan due to dev re-estimation, now targeting late September. |
| Discover new traffic channel #2 | Persona 3 | Deprioritized | %Traffic/Eligible +2pp | Q4-2026 | Deprioritized due to Cashier team resource constraints and performance test instability; rescheduled to Q4 2026. |
| Personalize offerings per users using big data | Persona 2 | Delay | %Submission/Traffic +2pp | Aug-26 | Kickoff delayed to end of June due to Data Science team prioritizing model optimization; estimated 2 months duration to complete. |
| New redirecting tactics for dropped customers | Persona 3 | Deprioritized | %Submission/Traffic +0.5pp | Q4-2026 | Deprioritized due to low expected impact; may be revisited in Q4 2026. |

Plan gaps without an active remediation initiative

%Approval Rate: 65% vs 70% plan (-5pp) — linked initiative #5.0 New score model version allows incremental more Eligible in existing segment & increasing Approval Rate already Live/Done but the residual gap is not closed; no active initiative is in the pipeline to close it — a remediation initiative / owner is needed.

Risks, dependencies & escalations

%Approval Rate: 65% vs 70% plan (-5pp); #5.0 New score model version allows incremental more Eligible in existing segment & increasing Approval Rate delivered its promise, but the residual gap is unowned with no active remediation initiative assigned.

#2.0 Add 1 partner with higher risk appetite: Delayed from Aug-26 to Sep-26 due to dev re-estimation, risking Q3 Eligible Base targets.

#10.0 Personalize offerings per users using big data: Delayed to Aug-26 due to Data Science prioritization, pushing Q3 submission rate improvements.

#12.0 Running year-end campaign: Not started with creative and budget unconfirmed, creating uncertainty for Q4 traffic volume.