CL – Biz – Report 2026.05

Cash Loan (CL) monthly business report  •  Reporting month: May 2026  •  Latest actual: May-26  •  Forecast month: Jun-26

Data basis. All figures are synthetic (invented company, partners, personas and numbers) drawn from the fake Annual Plan / KPI sheet and the fake Initiative Tracker (status as of end-May 2026). No confidential data is used. Structure follows the fixed four-part format; every section is split into Structural ceiling unlocks and Incremental acquisition / retention improvements.

KPI snapshot — Cash Loan funnel

| Metric (Cash Loan) | Unit | Apr-26 | May-26 | MoM | May Plan | vs Plan |
| --- | --- | --- | --- | --- | --- | --- |
| Total User Base | 000 | 61 | 64 | +5% | 64 | On plan |
| Eligible Base for Cash Loan | 000 | 12.2 | 22.3 | +84% | 22.3 | On plan |
| %Eligible / Total User Base | % | 20% | 35% | +15pp | 35% | On plan |
| Traffic to Landing Page | 000 | 4 | 7 | +84% | 9 | −24% |
| %Traffic / Eligible | % | 32% | 32% | 0pp | 42% | −10pp |
| Submission | 000 | 0.5 | 1.0 | +84% | 1.3 | −24% |
| %Submission / Traffic | % | 14% | 14% | 0pp | 14% | On plan |
| Approved | 000 | 0.3 | 0.7 | +117% | 0.9 | −24% |
| %Approval Rate | % | 55% | 65% | +10pp | 70% | −5pp |
| Average Ticket Size | VNDm | 110 | 110 | 0% | 110 | On plan |
| Disbursement Volume | VNDm | 32,945 | 71,543 | +117% | 101,124 | 71% |

Read: the eligible-base ceiling unlock landed in full (35%, on plan) and approval rate recovered +10pp — together driving Disbursement +117% MoM. Versus plan, Disbursement reached only 71% because traffic conversion stayed flat at 32% (vs 42% planned) and approval rate recovered to 65% (vs 70%).

# 1. Performance Overview and Analysis

Headline. May Disbursement was 71,543 VNDm — +117% MoM (Apr 32,945) but 71% of the 101,124 plan. The MoM surge is real and structural; the plan miss is a timing problem, not a demand problem. Approved volume more than doubled (0.3k→0.7k) on the back of a one-off eligible-base expansion and an approval-rate recovery, while the planned traffic-conversion step did not arrive because the initiative behind it slipped to June.

MoM bridge (fact). Disbursement +117% decomposes almost entirely into two compounding levers, with submission rate, traffic conversion and ticket all flat MoM: Eligible Base ×1.84 (12.2k→22.3k) and Approval Rate ×1.18 (55%→65%); 1.84 × 1.18 ≈ 2.17, i.e. +117%.

Plan-miss bridge (fact). Of the −29,581 VNDm gap to plan: ~24,077 (81%) is the traffic-conversion shortfall (%Traffic/Eligible 32% vs 42% planned) and ~5,503 (19%) is approval-rate under-recovery (65% vs 70%). Eligible base, submission rate and ticket size all hit plan, so the entire miss sits in two named, tracked initiatives.

Structural ceiling unlocks

- Eligible base — fully unlocked, on plan. %Eligible/Total rose 20%→35% (+15pp); eligible base 12.2k→22.3k. This reconciles exactly to two initiatives landing together: the new higher-risk-appetite partner (Persona 1, +10pp, confirmed live mid-May) and the v-next score model (Persona 2, +5pp eligible, delayed from April, confirmed live May). 10 + 5 = 15pp.

- Approval rate — recovered but below target. AR rose 55%→65% (+10pp), the uplift the v-next model promised. But absolute AR is 65% vs 70% plan: the −5pp dip incurred in March (a side-effect of the more-diverse offering, where users apply for larger tickets) has not been fully recovered. Remediation in progress — this is the structural item still off-plan.

- New data points — no May impact, on track for H2. New-segment scoring model (Persona 2, target Sep, +15pp eligible) is in development (scoping complete, build kicked off). It is the lever for the planned Oct step to 60% — not a May contributor.

Incremental acquisition / retention improvements

- Traffic conversion — flat, the single biggest reason for the plan miss. %Traffic/Eligible held at 32% (Apr 32%) vs 42% planned. The new product meant to unlock demand (Persona 3, +10pp) slipped May→June (UAT ran long: finish 25 May, deploy 31 May, launch June). Traffic volume still grew +84% — but purely mechanically, carried by the larger eligible base, not by better conversion. The previously-shipped traffic channel #1 (Persona 3, +2pp, live since March) is sustaining.

- Submission / funnel — stable at 14%, no new lever in May. %Submission/Traffic flat at 14%, holding the gains already banked from the landing-page revamp (Persona 1, +2pp, live Feb) and the more-diverse offering (Persona 1, +2pp, live Mar).

- Ticket size — flat at 110 VNDm. Holding the +10% step delivered in March by the more-diverse offering. No further ticket lever active in May; note this same initiative is the source of the AR drag flagged above.

# 2. Next Month (June) Run-Rate and Key Initiatives

Run-rate. June Disbursement run-rate is ~98,596 VNDm — +38% MoM and ~93% of the 106,180 plan. The gap to plan narrows sharply versus May because the delayed traffic-conversion step lands; the residual ~7% gap is the approval-rate recovery, still incomplete (run-rate assumes 65%, plan assumes 70%).

Structural ceiling unlocks

- Eligible base holds at 35% (23.5k), +5% MoM with user-base growth. No new eligible step due in June; next steps are Aug (45%) and Oct (60%).

- Approval-rate remediation continues to close the residual 65%→70% gap. Whether June reaches 70% is the swing factor on hitting plan.

Incremental acquisition / retention improvements

- New product unlocking demand (Persona 3) launches early June — the catch-up lever. Expected to lift %Traffic/Eligible 32%→42% (+10pp). This is the dominant driver of the June step-up and the item to protect against further slip.

- Personalization using big data (Persona 2, target Jul, +2pp submission) kicks off early June — dependent on the data-platform upgrade. Traffic channel #1 and the Feb/Mar conversion gains continue to be sustained.

# 3. Top 1 Priority for Next Month (June)

| # | Objective / lever | Initiative & owner | Target outcome & why it matters |
| --- | --- | --- | --- |
| 1 | Structural — traffic conversion | Launch new product that unlocks new demand (Persona 3) | Recover the +10pp %Traffic/Eligible (32%→42%) delayed from May. Largest single Disbursement lever for June; ~81% of May’s plan miss traces to this slip. Risk: it has already slipped once — guard the early-June launch date. |
| 2 | Structural — approval rate | Complete AR remediation (Persona 2) | Close the residual −5pp (65%→70%). Isolate and treat the higher-ticket side-effect from the diverse-offering initiative. Without this, June still misses plan by ~7%. |
| 3 | Structural — eligible pipeline | Advance Aug partner #2 due diligence & Sep new-segment model (Persona 1 / 2) | Protect the H2 engine: the Aug step to 45% and the Oct step to 60%. Both are currently Medium confidence; slippage here threatens the FY target far more than the May miss. |

Also in flight: kick off personalization (Persona 2) early June, gated on the data-platform upgrade; keep sustaining the live traffic and conversion gains.

# 4. Progress Toward Annual Plan

Structural ceiling unlocks

| Lever | What landed / what's next | Confidence | Status |
| --- | --- | --- | --- |
| Expand eligible pool | May: +15pp delivered (partner #1 +10pp, model v-next +5pp) → 35%, on plan. Next: partner #2 → 45% (Aug); new-segment model → 60% (Oct). | High (live) / Medium (Aug-Oct) | On track |
| Approval rate | v-next model delivered +10pp uplift; absolute AR 65% vs 70% target. Residual −5pp from Mar higher-ticket side-effect; remediation in progress. | High | Behind |
| New data points | New-segment scoring model in development (scoping done, build started); targets Sep, enabling the Oct eligible step to 60%. | Medium | On track |

Incremental acquisition / retention improvements

| Lever | What landed / what's next | Impact | Status |
| --- | --- | --- | --- |
| Traffic — new product (demand) | Slipped May→June; launches early June → +10pp %Traffic/Eligible (Persona 3). | +10pp | Delay→Jun |
| Traffic — channel #1 | Live since March; +2pp confirmed (30%→32%). Sustaining. | +2pp | Live |
| Traffic — channel #2 | Persona 3; planned Jul. Not yet started. | +2pp | Not started |
| Traffic — year-end campaign | Q4 (+5pp); planning to begin Q3, creative & budget not locked. | +5pp | Not started |
| Submission — landing page revamp | Live since Feb; +2pp confirmed (→12%→14%). Sustaining. | +2pp | Live |
| Submission / ticket — diverse offering | Live since Mar; +2pp submission (→14%) and +10% ticket (→110) confirmed. Note: source of −5pp AR drag. | +2pp / +10% | Live |
| Submission — personalization (big data) | Persona 2; planned Jul. Kickoff early June, gated on data-platform upgrade. | +2pp | Not started |
| Submission — redirect dropped users | Low expected impact (+0.5pp); deprioritized vs higher-impact work; may revisit Q4. | +0.5pp | Deprioritized |

YTD vs plan and FY outlook

YTD (Jan–May) Disbursement is 178,578 VNDm vs 230,480 plan (78%); the −51,902 cumulative gap is concentrated in April (−19,468) and May (−29,581). Both stem from the same root cause: the structural unlocks (eligible base + approval rate) and the traffic-conversion product all landed roughly one month later than the plan assumed. By May the eligible-base unlock had fully caught up to plan level; the remaining drag is traffic conversion (recovering in June) and the residual AR gap.

FY target of 1,879,675 VNDm remains achievable but is now back-loaded. It hinges on three things holding: (i) %Traffic/Eligible reaching and staying ≥42% from June, (ii) approval rate recovering to 70%, and (iii) the Aug (45%) and Oct (60%) eligible steps landing on time. The May miss is recoverable; a slip in the Aug/Oct eligible steps is not.

Risks, dependencies & escalations

- New-demand product (June launch) is load-bearing for the June run-rate and has already slipped once — a further slip directly compounds the YTD gap. [Watch closely]

- AR remediation: if the higher-ticket mix keeps dragging approval, the 70% plan is at risk. Action: isolate the side-effect of the diverse-offering initiative and quantify a clean AR baseline.

- Eligible steps #2 (Aug, 45%) and #3 (Oct, 60%) are Medium confidence and are the true FY engine — surface for escalation now, not in Q3.

- Personalization depends on the data-platform upgrade (external dependency); confirm the June kickoff is unblocked.

Prepared for hackathon use — synthetic data only. Generated to mirror the fixed CL report structure for the report auto-drafting tool.