## Initiatives tracker 5-2026
Initiatives Tracker — status as of end-May 2026
[5 empty] | (Not started, On Track, Delay, Deprioritized, Live) | (Flag if status change from last month) |  |  | (High, Medium, Low)
No | Initiative Names | Timing | Expected impact | PIC | Status | Status change | New timing (if applicable) | Details from that month | How confident
Strategic unlock
1 | Add 1 partner with higher risk appetite | May-26 | %Eligible/Total User Base +10pp | Persona 1 | On Track | No |  | - Integration and UAT finished in 04/2026 - Contract finalized in 04/2026 - Ready to pilot in mid 05/2026 => %Eligible/Total +10pp vs Apr | High
2 | Add 1 partner with higher risk appetite | Aug-26 | %Eligible/Total User Base +10pp | Persona 1 | On Track | No |  | Partner shortlisted, due diligence underway; on track for Aug launch. | Medium
3 | New modelling allows scoring new segments | Sep-26 | %Eligible/Total User Base +15pp | Persona 2 | On Track | No |  | Data-science scoping complete; model development kicked off, targeting Sep. | Medium
4 | Add new product that unlock new demand | May-26 | %Traffic/Eligible +10pp | Persona 3 | Delay | Yes | Jun-26 | Exp delay since UAT takes time than expected. New timeline to finish UAT: 25.May Deployment: 31.May => Ready to launch in Jun.26 | High
Incremental improvements
5 | New score model version allows incremental more Eligible in existing segment & increasing Approval Rate | Apr-26 | (1) %Eligible/Total User Base +5pp (2) %Approval Rate +10pp | Persona 2 | Delay | Yes | May-26 | Model v-next deployed May: +5pp Eligible and +10pp approval uplift as expected. But absolute approval ~65% vs 70% target — as AR decreased from Mar is not recovered, remediation in progress. | High
6 | Discover new traffic channel #1 | Mar-26 | %Traffic/Eligible +2pp | Persona 3 | Live | No
7 | Discover new traffic channel #2 | Jul-26 | %Traffic/Eligible +2pp | Persona 3 | Not started | No
8 | Revamp layout of Landing Page | Feb-26 | %Submission/Traffic +2pp | Persona 1 | Live | No
9 | Make product offerings more diverse | Mar-26 | (1) %Submission/Traffic +2pp (2) Average Ticket size +10% | Persona 1 | Live | No
10 | Personalize offerings per users using big data | Jul-26 | %Submission/Traffic +2pp | Persona 2 | Not started | No |  | Dependent on data-platform upgrade; kickoff planned early Jun.
11 | New redirecting tactics for dropped customers | Oct-26 | %Submission/Traffic +0.5pp | Persona 3 | Deprioritized | Yes | Q4/2026 | Low expected impact (+0.5pp); deprioritized vs higher-impact channel work; may revisit Q4.
12 | Running year-end campaign | Q4/2026 | %Traffic/Eligible +5pp | Persona 3 | Not started | No |  | Planning to begin Q3; creative & budget not yet locked.